## Individual Accounting
INDIVIDUAL ACCOUNTING
This document is an inventory of all artifacts created as part of the project. It should also list all work done during the course of the project.
Group work asset-author details
Individual accounting of work done for the project
All software development done by the team should be recorded in this file. This includes any models made.
Some columns may not be applicable if coding is not involved - building models, writing documentation.
Function name is usually class::method or Class.method
Task completed can be code development; testing; document writing; model creation; code review; .. Etc. If unsure, please ask at supervisor meeting
The work breakdown sheet (group declaration sheet) is a summary of the information in this file.
Only one copy of this file should be submitted. This file should be stored in a shared area where all team members have access.
Team members Name | Task completed | File Name | Function/model/document name | Lines of code/section of document | Comment lines | Purpose of function/model/document | Used/called/loaded by filename:functionName/model name | Estimated time for task | Actual time taken for task
STUDENT 1 | Implement new weapons |  |  |  |  | Use of friendlier weapons as game is not meant to be violent |  | 2hr | 1hr
Peter Neve | Left VR conrtoller compatibility |  |  |  |  | Allow left handers play game | Used by VR player prefab | 2hr | 1hr30min
| HUD display of life loss when targets missed (PC & VR) |  |  |  |  | Easy notification of good/bad target | Used by enemies | 4hr | 11hr
| Implementing weapon selection (VR) |  |  |  |  | Level difficulty | Used by player_HUD code & weaponSelection code | 2hr | 2hr40min
| Reload animations |  |  |  |  | Visual stimulus (movement) |  | 1hr | 1hr
| HUD display for hitting targets (PC & VR) Level1 |  |  |  |  | Visual stimulus | Used by individual enemies | 6hr | 9hr40min
| Enemy Animation |  |  |  |  | Visual stimulus (movement) | Used by individual enemies | 1hr | 30min
Menu
| VR compatible menus |  |  |  |  | Allow use to monuvour in VR |  | 1day | 1day
| Implementation |  |  |  |  | combine menus into full game |  | 1day | 3days
| Design/layout updates (Settings, Pause, Tutorial, GameOver) |  |  |  |  | Visual stimulus |  | 3hrs | 2hr
Level 1 re-implementation
| Layout/design |  |  |  |  | Visual stimulus |  | 1hr | 2hr
Level 2 implementation
| Update design/layout |  |  |  |  | Visual stimulus (more interesting) |  | 12hr | 1day
| Enemies | prefabs/enemies/level2 |  |  |  | Different enemies to keep player interested | Used by individual enemies | 1day | 1day
| HUD display for hitting targets (PC & VR) | prefabs/enemies/level2/Vranimation |  |  |  | Visual stimulus | Used by individual enemies | 1hr | 4hr
| Enemy Animations |  |  |  |  | Visual stimulus (movement) | Used by individual enemies | 2hr | 4hr
Level 3 implementation
| Update Ddesign/layout |  |  |  |  | Visual stimulus |  | 12hr | 1day
| Enemies | prefabs/enemies/level3/ |  |  |  | Different enemies to keep player interested | Used by individual enemies | 1day | 1day
| HUD display for hitting targets (PC & VR) | prefabs/enemies/level3/Vranimation |  |  |  | Visual stimulus | Used by individual enemies | 1hr | 4hr
| Enemy Animations |  |  |  |  | Visual stimulus (movement) | Used by individual enemies | 2hr | 2hr
| countdown code | StartCountDown.cs |  | ~70 |  | Breather between levels | Used by SceneLoader.cs | 4hr | 3hr
| Update Player_HUD code | Player_HUD.cs |  | ~120 of 332 |  | Allows game to function | Used by Player prefab |  | 4hr
| Update enemy Codes | Enemy Types |  | ~20 |  | Allows enemies to behave | Used by individual enemies |  | 2hr
Demonstration video
| Transition Screen |  |  |  |  | Visual stimulus | Used by SceneLoader.cs | 30min | 30min
| Update Level trasition code | SceneLoader.cs |  | ~10 of 70 |  | Greater functionality | Used by SceneLoader.cs | 1hr | 1hr
| Update level loader code | LevelLoader.cs |  | ~20 of 100 |  | Greater functionality | Used by Gameover,Pause | 30min | 30min
| Audio implentation |  |  |  |  | Audio stimulus | Used by Enemies, Player, weapon | 1hr | 2hr
STUDENT 2 | Task completed | File Name | Function/model/document name | Lines of code/section of document | Comment lines | Purpose of function/model/document | Used/called/loaded by filename:functionName/model name | Estimated time for task | Actual time taken for task
Kushal Ganji | Level 2 Layout/Design | Level2Start | [5 empty] | 10H | ~15H
| Level 3 Layout/Design | Level3Start | [5 empty] | 2H | 3H
Find+Import Assets:
| - Asteroids | AsteroidsPack_Level3 |  |  |  | Level 3 enemy |  | 15min | 15min
| - Fish + Shark underwater pack | Fish+Shark_UnderwaterPack |  |  |  | Level 2 enemies |  | 15min | 15min
| - Lightpole | lightpole |  |  |  | asset added to the jetty |  | 15min | 15min
| - Space Elemental | Space_Elemental_Level3 |  |  |  | Level 3 enemy |  | 15min | 15min
| Level Transition Code | LevelTransition |  |  |  | Change the level from level 1 to 2 to 3 when the player reaches a certain point range |  | 5H | 6H 30min
| Asset Retexturing |  |  |  |  | Issue with textures on imported assets, so manually retextured assets |  | 5H | 4H
STUDENT 3 | Task completed | File Name | Function/model/document name | Lines of code/section of document | Comment lines | Purpose of function/model/document | Used/called/loaded by filename:functionName/model name | Estimated time for task | Actual time taken for task
Yoshitha Premarathna | Music and SFX | [6 empty] | 2 Days | 1 Day
| Composed Jetty Preserver Main Sound Track | Jetty Preserver Soundtrack.mp3 |  |  |  | Background Music for the Game | Used by AudioManager.cs
| Background SFX for All Levels | Ocean Background.mp3, Underwater_background.mp3, Alien_Background.mp3 |  |  |  | Different Level background sound effects. | Used by SFXAudioManager.cs
| Composed Weapon Sounds | Weapon 1.mp3, Weapon 2.mp3, Weapon 3.mp3, Weapon Acquired.mp3 |  |  |  | Used for teleport guns | Used by SFXAudioManager.cs
| Composed Enemy Hit Sounds | Enem_Hit_1.mp3, Enemy_hit_2.mp3, Enemy_Hit_3.mp3 |  |  |  | Used for enemies | Used by SFXAudioManager.cs
| Recorded Train Sound | Train.mp3 |  |  |  | In game | Used by SFXAudioManager.cs
| Menu Sounds | Button_Click.mp3, BtnClickSound.cs |  |  |  | Menus and other buttons | Used by SFXAudioManager.cs | 1 Day Total | 1 Day
Menu Codes
| Coded all the functions for Main Menu | Tutorial.cs | [5 empty] | 5 Hours | 3 Hours
| Coded all the functions for Settings Menu | AudioManager.cs, SFXSoundManager.cs | [5 empty] | 5 Hours | 3 Hours
| Coded all the functions for Pause Menu Menu | PauseMenuNew.cs | [5 empty] | 5 Hours | 3 Hours
| Coded all the functions for Game Over menu | [6 empty] | 5 Hours | 3 Hours
| Menu Layouts |  |  |  |  | Design of all the Menus
Creating the layout of Start Menu
Creating the layout of Settings Menu
Creating the layout of Pause Menu
| Creating the layout of Game Over | [6 empty] | 2 Days Total | 1 Day
| Coded Game Load Function | LevelLoader.cs, LevelSaver.cs |  |  |  | Click the load button to load the last played frame. |  | 2 Hours | 2 Hours
| Coded High score Funtion | GameMenuController.cs |  |  |  | In Game over menu. |  | 2 Hours | 1 Hours
| Coded a Loading Screen | LevelLoader.cs |  | ~54 - 68 |  | Loading slider. | called by LoadAsynchronously() | 15 Minutes | 15 Minutes
| Credits Animation | [6 empty] | 30 Minutes | 15 Minutes